## Risk Analysis
| Risk | Impact | Probability | Risk Score | Probability/Impact | Insignificant | Minor | Significant | Major | Severe
1 | · Poor quality code | 2 | 4 | 8 |  | (1) | (2) | (3) | (4) | (5)
2 | · Technical issues with third-party integrations | 3 | 3 | 9 | Almost certain (5)
3 | · Team member leaving | 2 | 3 | 6 | Highly Likely (4)
4 | · Uscope creep | 3 | 4 | 12 | Likely (3) |  |  | Technical issue | scope creepe
5 | · Client feedback delays | 1 | 1 | 1 | Unlikely (2) |  |  | Team member leaving | poor quality
6 |  |  |  |  | Highly unlikely (1) | Client feedback delays
7
Ref | Risk Mitigation Strategies
Scope creep: Regular communication with the client, clearly defined project scope, and change contr
Technical issues: Thorough testing, contingency plans for critical components, and close collaboration with third-party vendo
Client feedback delays: Set clear expectations with the client regarding feedback deadlines and follow-up reminders.
Team member turnover: Cross-training team members, documenting processes, and maintaining a positive work environment to reduce turnover.

## Lookups
Impact | Probability
1 | 1
2 | 2
3 | 3
4 | 4
5 | 5